## issue
number | name | description | project | type | corrective_action | cost | status | create_time
IR00001 | Incorrect PCB layout | Connectivity of PCB-type inductor in layout is incorrect. | P09-001 | PCB | YES | 0 | CLOSED | 2013-01-02
IR00002 | Difficult assembly procedure | Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly. | P09-001 | ASSY | YES | 0 | CLOSED | 2013-01-03