## issue
number	name	description	project	type	corrective_action	cost	status	create_time
IR00001	Incorrect PCB layout	Connectivity of PCB-type inductor in layout is incorrect.	P09-001	PCB	YES	0	CLOSED	02-01-2013
IR00002	Difficult assembly procedure	Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly.	P09-001	ASSY	YES	0	CLOSED	03-01-2013

## issue-tryton
number	name	description	project	type	corrective_action	cost	status	create_time
IR00001	Incorrect PCB layout	Connectivity of PCB-type inductor in layout is incorrect.	P09-001	PCB	YES	0	CLOSED	2013-01-02
IR00002	Difficult assembly procedure	Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly.	P09-001	ASSY	YES	0	CLOSED	2013-01-03