## issue
id | name | description | owner_id | part_id | project_id | requestor_id | status_id | stock_id | type_id | create_time | create_user_id | update_time | update_user_id
1 | Incorrect PCB layout | Connectivity of PCB-type inductor is incorrect. | 3 | 15 | 2 | 3 | 1 |  | 0 | 2014-09-17 | 22 | 2014-09-17 | 22
2 | Difficult assembly procedure | Manufacturing staff report assembly of wireless unit is difficult to assemble and test due to copper-side-up orientation of PCA. Suggestion is to orient PCA component-side up providing for full access to components for more effective visual inspection and easier troubleshooting after assembly. | 3 | 1 | 2 | 3 | 1 |  | 1 | 2014-09-17 | 22 | 2014-09-17 | 22
3 | No field spares kit. | Customers are requesting we provide a field spares kit with most-commonly used repair items for convenience of repair technicians. | 6 |  | 2 | 6 | 1 |  | 1 | 2014-09-17 | 11 | 2014-09-17 | 11
Formulas:
update_time = [create_time]

## issue_status
id | value | status | description
1 | 0 | NOT STARTED | Issue has not been started
2 | 1 | STARTED | Issue has been started
3 | 2 | FINISHED | Issue has been finished (resolved)

## issue_type
id | value | type | description
1 | 0 | BUG | Deficiency in behavior compared to requirements.
2 | 1 | FEATURE | Desired behavior, but not required.
3 | 2 | TASK | Activity requiring effort to resolve (neither bug or feature)