## issue
number	name	description	project	type	corrective_action	cost	status	create_time
IR00001	Incorrect PCB layout	Connectivity of PCB-type inductor in layout is incorrect.	P09-001	PCB	YES	0	CLOSED	02-01-2013
IR00002	Difficult assembly procedure	Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly.	P09-001	ASSY	YES	0	CLOSED	03-01-2013

## issue-tryton
number	name	description	project	type	corrective_action	cost	status	create_time
IR00001	Incorrect PCB layout	Connectivity of PCB-type inductor in layout is incorrect.	P09-001	PCB	YES	0	CLOSED	2013-01-02
IR00002	Difficult assembly procedure	Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly.	P09-001	ASSY	YES	0	CLOSED	2013-01-03

## issue-mantis
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
18	Default	fmason	bjenks	@0@	minor	have not tried		General	1/1/2013				public	9/6/2014	Make PCB corrections	assigned	open
21	Default	fmason	fmason	@0@	minor	have not tried		General	1/4/2013				public	9/5/2014	Release field service kit	assigned	open
20	Default	fmason	mdelazes	@0@	minor	have not tried		General	1/3/2013				public	9/5/2014	Reduce cost and improve quality	assigned	open
19	Default	fmason	jsharp	@0@	minor	have not tried		General	1/2/2013				public	9/5/2014	Release marketing assembly	assigned	open
17	Default	fmason	bjenks	@0@	minor	have not tried		General	12/31/2012				public	9/5/2014	Release prototype PCA	assigned	open