## uid-lookup
Ldap-cn	uid
Barcoe Jenks	bjenks
Barton Swift	bswift
Bub Armstrong	barmstrong
Frank Mason	fmason
Garret Jackson	gjackson
Hank Baldwin	hbaldwin
Helen Randall	hrandall
Jacab Wood	jwood
James Period	jperiod
Jennie Haddon	jhaddon
Jennie Morse	jmorse
John Sharp	jsharp
Martha Baggert	mbaggert
Mary Nestor	mnestor
Minnie Blair	mblair
Miquel DeLazes	mdelazes
Ned Newton	nnewton
Rad Sampson	rsampson
Sarah Malloy	smalloy
Tom Swift	tswift
Wakefield Damon	wdamon
William Crawford	wcrawford

## todolist-scc_edited
Position	Title	Task ID	Parent Task ID	Priority	Risk	Percent Complete	Creation Date	Created By	Created-uid	Modified Date	Start Date	Due Date	Allocated To	Allocated-uid	Status	Category	Cost	Comments
1	Release prototype PCA	1		5	0	0	2012-12-31	Frank Mason	fmason	2014-09-06	2012-12-31	2013-01-01	Barcoe Jenks	bjenks	Open	Wireless	0	Release PN 20000004 Rev 00 with child parts and sub-assemblies for building a small number of prototype units. Assembly to include functional PCA, earphone, wire for stubby antenna and preliminary user manual (NO enclosure). Manufacturing process documentation to include product part breakdown structure diagram, work instruction for packing beta test units and a work instruction for fabricating PN 20000001 (custom inductor).
2	Make PCB corrections	2		5	0	0	2013-01-01	Frank Mason	fmason	2014-09-06	2013-01-01	2013-01-02	Barcoe Jenks	bjenks	Open	Wireless	0	Revise schematic to correct connectivity of PCB-type inductor; revise PCB design to correct the inductor layout and mechanical dimensions (and generate new CAM files). Create PCB master drawing. Create PCA assembly drawing and work instruction. Update work instruction for custom inductor PN 20000001 to meet revised format requirements (rev level will not change as fit/form/function remains the same).
3	Release marketing assembly	3		5	0	0	2013-01-02	Frank Mason	fmason	2014-09-06	2013-01-02	2013-01-03	John Sharp	jsharp	Open	Wireless	0	Re-structure product to meet product release requirements, including creation of new top-level marketing assembly part number. Product to include enclosure with hardware, user manual and earphone to be moved to marketing assembly, stubby antenna removed, user manual to be updated.
4	Reduce cost and improve quality	4		5	0	0	2013-01-03	Frank Mason	fmason	2014-09-06	2013-01-03	2013-01-04	Miquel DeLazes	mdelazes	Open	Wireless	0	Invert PCB in enclosure to aid assembly and test (requiring modifications to enclosure base and lid, including artwork). Update PCA assembly diagram and work instruction, update enclosure-level assembly diagram and work instruction.
5	Release field service kit	5		5	0	0	2013-01-04	Frank Mason	fmason	2014-09-06	2013-01-04	2013-01-05	Frank Mason	fmason	Open	Wireless	0	Create kit of parts found typically useful for field service.