## issue
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version		Description
30	Aircraft Wireless 09-001	jperiod	fmason	normal	minor	always		General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Customers asking for field spares kit.	assigned	open			Connectivity of PCB-type inductor in layout is incorrect.
29	Aircraft Wireless 09-001	tswift	bjenks	normal	minor	always		General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Difficult assembly procedure	assigned	open			Difficult to assemble and test PCA due to copper-side-up orientation. Orienting PCA component-side up allows for full access to components for debugging after assembly.
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always		General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried		General	2012-12-31				public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed			Release PN 20000004 Rev 00 with child parts and sub-assemblies for building a small number of prototype units. Assembly to include functional PCA, earphone, wire for stubby antenna and preliminary user manual (NO enclosure). Manufacturing process documentation to include product part breakdown structure diagram, work instruction for packing beta test units and a work instruction for fabricating PN 20000001 (custom inductor).
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried		General	2013-01-01				public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open			Revise schematic to correct connectivity of PCB-type inductor; revise PCB design to correct the inductor layout and mechanical dimensions (and generate new CAM files). Create PCB master drawing. Create PCA assembly drawing and work instruction. Update work instruction for custom inductor PN 20000001 to meet revised format requirements (rev level will not change as fit/form/function remains the same).
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried		General	2013-01-02				public	2014-09-17	Iteration 3 - Release marketing assembly	assigned	open			Re-structure product to meet product release requirements, including creation of new top-level marketing assembly part number. Product to include enclosure with hardware, user manual and earphone to be moved to marketing assembly, stubby antenna removed, user manual to be updated.
20	Aircraft Wireless 09-001	fmason		none	minor	have not tried		General	2013-01-03				public	2014-09-17	Iteration 4 - Reduce cost and improve quality	assigned	open			Invert PCB in enclosure to aid assembly and test (requiring modifications to enclosure base and lid, including artwork). Update PCA assembly diagram and work instruction, update enclosure-level assembly diagram and work instruction.
21	Aircraft Wireless 09-001	fmason	fmason	none	minor	have not tried		General	2013-01-04				public	2014-09-17	Iteration 5 - Release field service kit	assigned	open			Create kit of parts found typically useful for field service.

## csv-1
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed	0

## csv-2
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed	0
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed	0
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2013-01-01	0	0	0	public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open	0

## csv-3
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed	0
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2013-01-01	0	0	0	public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open	0
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed	0
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-02	0	0	0	public	2014-09-17	Iteration 3 - Release marketing assembly	assigned	open	0

## csv-4
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed	0
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2013-01-01	0	0	0	public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open	0
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed	0
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-02	0	0	0	public	2014-09-17	Iteration 3 - Release marketing assembly	assigned	open	0
29	Aircraft Wireless 09-001	tswift	bjenks	normal	minor	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Difficult assembly procedure	assigned	open	0
20	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-03	0	0	0	public	2014-09-17	Iteration 4 - Reduce cost and improve quality	assigned	open	0

## csv-5
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed	0
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2013-01-01	0	0	0	public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open	0
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed	0
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-02	0	0	0	public	2014-09-17	Iteration 3 - Release marketing assembly	assigned	open	0
29	Aircraft Wireless 09-001	tswift	bjenks	normal	minor	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Difficult assembly procedure	assigned	open	0
20	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-03	0	0	0	public	2014-09-17	Iteration 4 - Reduce cost and improve quality	assigned	open	0
30	Aircraft Wireless 09-001	jperiod	fmason	normal	minor	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Customers asking for field spares kit.	assigned	open	0
21	Aircraft Wireless 09-001	fmason	fmason	none	minor	have not tried	0	General	2013-01-04	0	0	0	public	2014-09-17	Iteration 5 - Release field service kit	assigned	open	0

## issue-tryton
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category
30	Aircraft Wireless 09-001	jperiod	fmason	normal	minor	always	0	General
29	Aircraft Wireless 09-001	tswift	bjenks	normal	minor	always	0	General
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General
20	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General
21	Aircraft Wireless 09-001	fmason	fmason	none	minor	have not tried	0	General

## issue-mantis
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
30	Aircraft Wireless 09-001	jperiod	fmason	normal	minor	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Customers asking for field spares kit.	assigned	open
29	Aircraft Wireless 09-001	tswift	bjenks	normal	minor	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Difficult assembly procedure	assigned	open
28	Aircraft Wireless 09-001	tswift	bjenks	high	block	always	0	General	2014-09-17	N/A	N/A	N/A	public	2014-09-17	Incorrect PCB layout	closed	fixed
17	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2012-12-31	0	0	0	public	2014-09-17	Iteration 1 - Release prototype PCA	closed	fixed
18	Aircraft Wireless 09-001	fmason	bjenks	none	minor	have not tried	0	General	2013-01-01	0	0	0	public	2014-09-17	Iteration 2 - Make PCB corrections	assigned	open
19	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-02	0	0	0	public	2014-09-17	Iteration 3 - Release marketing assembly	assigned	open
20	Aircraft Wireless 09-001	fmason		none	minor	have not tried	0	General	2013-01-03	0	0	0	public	2014-09-17	Iteration 4 - Reduce cost and improve quality	assigned	open
21	Aircraft Wireless 09-001	fmason	fmason	none	minor	have not tried	0	General	2013-01-04	0	0	0	public	2014-09-17	Iteration 5 - Release field service kit	assigned	open